## Michael Teixeira
To-do list
To be completed by: |  | November 18th, 2019 |  | Name: Mike Teixeira
Deadline: |  | November 18th, 2019 |  | Date: November 25th, 2019
% done | Phase | Start By | Original Due By | Revised Due By (Mike Checks Your Work) | Number Of Actual Days To Complete (inclusive)
100% | Read Chapter 1 for review (Take Notes) | 2019-11-25 | 2019-11-26 |  | 1 Days
100% | Read the Data from the UploadFile.CoursesSpring2019 table | 2019-11-25 | 2019-11-26 |  | 1 Days
100% | Design Database using SQLDBM | 2019-11-25 | 2019-11-26 |  | 1 Days
100% | Create Schemas w/ appropriate names | 2019-11-27 | 2019-11-28 |  | 1 Days
100% | Create the Process.TableWorkFlow table | 2019-11-27 | 2019-11-28 |  | 1 Days
100% | Create the stored procedure Process.usp_TrackWorkFlow to track the work done on each part of the project | 2019-11-27 | 2019-11-28 |  | 1 Days
100% | Create the Department Table | 2019-11-30 | 2019-11-30 |  | 1 Days
100% | Create the Instructor Table | 2019-11-30 | 2019-11-30 |  | 1 Days
100% | Create the DepartmentInstructor Table | 2019-11-30 | 2019-11-30 |  | 1 Days
100% | Create the ModeOfInstruction Table | 2019-11-30 | 2019-11-30 |  | 1 Days
100% | Create the InstructorModeOfInstruction Table | 2019-11-30 | 2019-11-30 |  | 1 Days
100% | Create the RoomLocation Table | 2019-11-30 | 2019-11-30 |  | 1 Days
100% | Create the BuildingLocation Table | 2019-11-30 | 2019-11-30 |  | 1 Days
100% | Create the Course Table | 2019-11-30 | 2019-11-30 |  | 1 Days
100% | Create the ClassDay Table | 2019-11-30 | 2019-11-30 |  | 1 Days
100% | Create the TimeSlot Table | 2019-11-30 | 2019-11-30 |  | 1 Days
100% | Create the ClassRoom Table | 2019-11-30 | 2019-11-30 |  | 1 Days
100% | Create the stored procedure Modify.usp_TruncateAllTables to drop all table data | 2019-12-01 | 2019-12-01 |  | 1 Days
100% | Create the stored procedure Modify.usp_DropAllForeignKeys | 2019-12-01 | 2019-12-01 |  | 1 Days
100% | Create the stored procedure Modify.usp_AddAllForeignKeys | 2019-12-01 | 2019-12-01 |  | 1 Days
100% | Create the Sequence Object for the each Table | 2019-12-01 | 2019-12-01 |  | 1 Days
100% | Load the Department Table with the data from the UploadFile.CoursesSpring2019 | 2019-12-01 | 2019-12-01 |  | 1 Days
100% | Load the Instructor Table with the data from the UploadFile.CoursesSpring2019 | 2019-12-01 | 2019-12-01 |  | 1 Days
100% | Load the DepartmentInstructor Table with an inner join on the department and instructor table | 2019-12-01 | 2019-12-01 |  | 1 Days
100% | Load the ModeOfInstruction Table with the data from the UploadFile.CoursesSpring2019 | 2019-12-01 | 2019-12-01 |  | 1 Days
100% | Load the InstructorModeOfInstructor Table with the data from the UploadFile.CoursesSpring2019 | 2019-12-01 | 2019-12-01 |  | 1 Days
100% | Load the Room Table with the data from the UploadFile.CoursesSpring2019 | 2019-12-01 | 2019-12-01 |  | 1 Days
100% | Load the BuildingLocation Table with the data from the UploadFile.CoursesSpring2019 | 2019-12-01 | 2019-12-01 |  | 1 Days
100% | Load the YearOfEnrollment table with the data from the UploadFile.CoursesSpring2019 | 2019-12-01 | 2019-12-01 |  | 1 Days
100% | Load the Course Table with the data from the UploadFile.CoursesSpring2019 | 2019-12-01 | 2019-12-01 |  | 1 Days
100% | Create a single stored procedure that loads in each table at once | 2019-12-04 | 2019-12-04 |  | 1 Days
100% | Setup JDBC Java Project | 2019-12-06 | 2019-12-06 |  | 1 Days
100% | Establish connection to localhost | 2019-12-06 | 2019-12-06 |  | 1 Days
100% | 1.Show all instructors who are teaching in classes in multiple departments | 2019-12-06 | 2019-12-06 |  | 1 Days
100% | 2. How many instructors are in each department? | 2019-12-06 | 2019-12-06 |  | 1 Days
100% | 3. How may classes that are being taught that semester grouped by course and aggregating the total enrollment, total class limit and the percentage of enrollment. | 2019-12-06 | 2019-12-06 |  | 1 Days
100% | 4. 3 more queries of your choice and their proposition. | 2019-12-06 | 2019-12-06 |  | 1 Days